## Sheet1
Task Assignment - Sprint 1
Story ID | Story Title | Asignee | Status | Importance
1 | Accoutn Registration | Braydon | Complete | Must
3 | Media Vault Login | Braydon | Complete | Must
4 | View My Files | Lewis | Complete | Must
5 | Download My Files | Lewis | Complete | Must
6 | Upload a File - file explorer | Yoon | Complete | Must
6B | Upload a file - drag and drop | Yoon | Complete | Should Have
18 | View/Edit Account Details | Yoon | Complete | Must
19 | Reset Forgotten Password | Braydon | Complete | Could Have
20 | Log Out | Yoon | Complete | Must
7 | Add Folder | Lewis | Complete | Must
11 | Delete file | Braydon | Complete | Must
Task Assignment - Sprint 2
Story ID | Story Title | Asignee | Status | Importance
8 | Open a PDF File | Lewis | Complete | Must
8B | Open my eBook File | Yoon | Complete | Could Have
9 | Open my Audio File | Yoon | Complete | Must
10 | Open my Picture File | Lewis | Complete | Must
10B | Open my Folder | Lewis | Complete | Must
14 | Add/Edit Meta Data to Uploaded File | Yoon | Not Complete | Must
16 | Manually Add Meta Data when Uploading File | Braydon | Not Complete | Must
16B | Automatically Add Meta Data when Uploading File | Lewis | Complete | Could Have
13 | Search a File | Lewis | Complete | Must
17 | Sort Files by Meta Data | Lewis | Not Complete | Must
17B | Sort Files by Name | Braydon | Complete | Must
17C | Sort Files by Date | Braydon | Not Complete | Must