## Sheet1
Task Assignment - Sprint 2
Story ID | Story Title | Asignee | Status | Importance
8 | Open a PDF File | Lewis | Complete | Must
8B | Open my eBook File | Yoon | Not Complete | Could Have
9 | Open my Audio File | Yoon | Not Complete | Must
10 | Open my Picture File | Lewis | Complete | Must
10B | Open my Folder | Lewis | Not Complete | Must
14 | Add/Edit Meta Data to Uploaded File | Yoon | Not Complete | Must
15 | Manually Add Meta Data when Uploading File | Braydon | Complete | Must
16 | Automatically Add Meta Data when Uploading File | Lewis | Not Complete | Could Have
13 | Search a File | Lewis | Complete | Must
17 | Sort Files by Meta Data | Lewis | Not Complete | Must
17B | Sort Files by Name | Braydon | Not Complete | Must
17C | Sort Files by Date | Braydon | Not Complete | Must