## Sheet1
[9 empty] | MoSCoW | 4 members - 1 point = 8 hours
Story Ref # | Feature | Story Title | As a | I want to | so that | Acceptance criteria | Questions | Comments | Business Priority | Story Point Estimate | Status | Release | Iteration
EPIC | Media Vault | Media Vault | User | I want a program that lets me store and access my personal files from any device | I do not have to use one device to access my files | A webservice is availiable to store files on
Account Setup/features
1 | Register | Registering an account | User | be able to see a page to register an account | i can set up my cloud-based system for my media storage | A form should appear to our website's address with a registration form |  | Set up database, set up website server, and then create a registration page | Must | 4
2 | Register | Registering an account | User | I want to be able to enter my email in | So that this can be my login ID | A form should appear to our website's address with a registration form |  | The field to enter the email needs to sent the email to the database, there will be an error if the user email is already taken | Must | 1
3 | Register | Registering an account | User | I want to be able to enter my password in twice | So that I can set my password for my account | A form should appear to our website's address with a registration form |  | The fields to enter the password needs to make sure the password has been entered in correctly, has proper validation and sends to the database | Must | 1
4 | Register | Registering an account | User | I want to receive a confirmation email | So that I can confirm that my account is linked to the email I provided | A confirmation email should be sent out to the email address the user registered with |  | Set up a service that sends out an email to the address that the user has provided | Must | 2
5 | Register | Registering an account | User | I want to confirm my account through the confirmation email | So that I can confirm that my account is linked to the email I provided | A confirmation link should be in the email that was sent |  | The email sent out needs to have a link that activates the user's account, and takes them back to the MediaVault | Should
6 | Log in | Signing in an account | User | be able to sign in | I can access my account to store my media files | A prompt should be present to enter user details to log in |  | Matches the user's password and email with what is stored in the database. If it is correct, the user is taken to the MediaVault home page. If it is incorrect, the user is prevented with an error message saying that their details are incorrect | Must | 2
7 | Log in | User Dashboard | User | To see a user dashboard with my files once I have signed in | So I that I can navigate the website | A user dashboard should appear, showing: The cloud files and an options panel |  | The dashboard will need to link with the database to fetch all the user's files. We're only fetching the file names and displaying them (Folders?) | Must | 2
8 | User Dashboard | User Dashboard - File Panel | User | See specific file attributes, such as the file type, date created, file size and any meta data I have added to the file | So that I can see this extra information on the file easily | Next to the file names should be these categories |  | We will need a table to store the metadata for the file, and then we will have to display that information on the webstie | Should
9 | User Dashboard | User Dashboard - File Panel - sort | User | Sort my files (e.g. by date, or a meta data tag a file has) | So that I can organise the files | The files should be sorted in the order of the specific category chosen, similar to windows file explorer at the top |  | The website will need a button or option to allow the user to sort their files. Will require a sorting algorightm, this will be different depending on what we want to sort the file by: date, name or meta data | Should
10 | User Dashboard | User Dashboard - File Panel Search | User | Search through my files I have uploaded | They are easier to access and I can find what I am searching for | The website will show files with meta tags that relate to the search criteria |  | Will need to implement a search bar, and then search through the database for what was entered | Could
11 | User Dashboard | User Dashboard - File Panel | User | Be able to click on a link that would take me to my person account details | So that I can edit and view my account details | A button that signifies the user's personal details should appear |  |  | Want
12 | User Dashboard | User Dashboard - Account details | User | Be able to see an option that lets me change my password | So that I can update if needed | Pasword Resets to what they want |  | Implement a button that takes the user to a screen that lets them change their password | Must | 1
13 | User Dashboard | User Dashboard - Account details - Change Password | User | See fields that require me to enter my old password in and my new password in twice | So that I can update my password safely | Pasword Resets to what they want |  | Create 3 fields, one for the old password, 2 for the new password. Will need to confirm that the old password is right, and then change the password once submitted. | Must | 2
14 | User Dashboard | User Dashboard - Account details - Change Email | User | Be able to change my email | So that I can update if needed | Change email to the new one |  |  | Should
15 | User Dashboard | User Dashboard - Account details - Change Email | User | See a field to enter my email into | So that I can update if needed | Change email to the new one |  |  | Should
16 | User Dashboard | User Dashboard - Account details - Change Email | User | Receive a confirmation email to the new email address | so that I can confirm this email | Change email to the new one |  |  | Should
17 | User Dashboard | User Dashboard - File Panel | User | Right click on a file to edit its details | So that I can change the file name or add meta data tags | Renames the file |  |  | Could
18 | User Dashboard | User Dashboard - File Panel | User | See an option to edit the file name, and then the user can rename the file once clicked (where the name of the file is displayed) | So that the user can rename the file | Renames the file |  |  | Should
19 | User Dashboard | User Dashboard - File Panel | User | See an option to add meta tag options, and then the user can can edit the meta tags in a window that opens up | So that the user can add/edit the file's meta tags | Change email to the new one |  |  | Should
20 | Upload | Uploading files | User | be able to upload files I want to the server through an upload button, and add their meta data in the process | I can access and download later on any devices, and the meta data should be stored in our database | The user should be able to upload files by using the upload button/or by drag and drop function |  | We will need a button that opens a file explorer, and the user can pick the fild that they want to upload. A window that lets the user pick the meta data should appear. The file info and meta data should be added to our file. | Must | 8
21 | Upload | Uploading files | User | I want to upload files by dragging and dropping a file into the file panel view | So that I can upload the document easily(multiple allowed) | Uploads the file to the cloud, and the user can access it |  |  | Want
22
23 | Upload | Uploading files | User | I want to be able to add a folder | So that I can add files to this folder | lets the user create and name a folder |  |  | Could
24 | Download | Downloading files | User | be able to download the files | I can use and/or store files on any other devices | Download should automatically start once the user presses the download button |  |  | Must
25 | Download | Downloading files | User | be able to select and download multiple files | So that I can download more files at once |  |  |  | Could
26 | Reset Password | Add reset password functionality | User | Reset my password if I have forgotten it button that takes you to a forget your password page | So that I can log in if I have forgotten my password | The user should receive an email to reset their password |  |  | Must | 1
27 | Reset Password | Add reset password functionality | User | Receive a confirmation email with a link that resets my password | So that I can log in if I have forgotten my password | The user should receive an email to reset their password |  |  | Must | 4
28 | Reset Password | Add reset password functionality | User | Be able to enter a new password from the reset email that has been sent to me | So that I can log in if I have forgotten my password | The user should be taken to a screen to reset their password |  |  | Must | 1
29 | Music | Listen to audio | User | be able to open my audio files | I could listen to them and not download them | MP3/AVI player to allow audio files to be played |  |  | Must | 8
30
31 | Pictures | View pictures | User | be able to immidiately access pictures | I can view pictures without having to download them | A browser plug-in should allow the user to see pictures |  |  | Must | 8
32 | Ebook | Read an uploaded ebook | User | Open an ebook on the website | So that I can read it on the website | The ebook should open and the pages can be read |  |  | Should